## Summary
Wayvida Books - build completion status
Assessed prototype completeness per module, from the 43 navigation destinations in src/Navigation.jsx and the page dispatch in src/App.jsx. The percentages are an assessment, not a tracked metric, and every figure on this sheet is calculated from the Pages tab.
Module | Completion | Pages | Main gap
Dashboard | 85% | 1 | Seeded demo data only: metrics, charts and the task list are not read from posted journals.
Accounting | 91.25% | 4 | Four register-complete pages; remaining gaps are mapping administration and recurring-post automation.
Inventory | 89% | 2 | Two pages; stock movements post to journals, but valuation methods and locations are single-track.
Sales | 90.2% | 5 | Strongest module: five destinations share the register row, document previews and status pills.
Purchases | 82.67% | 6 | Full service layer (orders, receipts, bills, debit notes, payments), but the registers still sit on their own headers.
Banking | 77.25% | 4 | CSV statement import, matching rules and reconciliation are real; there is no live bank feed.
Expenses | 69% | 2 | Create and post only: no approval chain and no reimbursement payout.
Assets | 65% | 3 | Register and depreciation post; disposal and revaluation are absent.
Tax | 60% | 2 | Read-only GST and TDS monitors: no return or challan output.
Reports | 75.4% | 10 | Ten destinations, mostly read-only; exports and comparative periods are uneven.
Settings | 70.67% | 3 | 18 sections persist locally; enforcement inside the business modules is partial.
Help | 65% | 1 | Static guidance content.
All modules (page-weighted) | 78.33% | 43
How the percentage is assessed
Every page is scored on what the repository actually contains: a real store or service, a create/edit workflow, a register with search and filters, a drill-down detail, document output where the document type needs one, and its own tests. Pages without a register, such as reports and settings, are scored on the dimensions that apply to them.
Completion means prototype completeness, not production readiness. Production readiness is roughly 15-20 percent: persistence is browser storage, roles are simulated, and no control can be enforced server-side. See docs/KNOWN-GAPS-AND-ROADMAP.md for that track.
Sources: src/Navigation.jsx, src/App.jsx, each module component and its store or service, src/register-head.js (11 of 33 table pages migrated to the shared register row), and the 80 test files under tests/. Assessed 2026-09-21.

## Pages
Page-level completion
One row per navigation destination. Status is calculated from the completion column, so editing a percentage updates the sheet.
Module | Page | Route key | Rendered by | Completion | Status | Main gap | Test files
Dashboard | Dashboard | Dashboard | ExactDashboard | 85% | Prototype-complete | Metrics, charts and tasks are seeded demo data. | 2
Accounting | Chart of Accounts | Chart of Accounts | AccountWorkspace | 95% | Prototype-complete | No .xlsx import; account-mapping admin screen still planned. | 11
Accounting | Journal Entries | Journal Entries | JournalEntriesPro | 92% | Prototype-complete | No bulk edit; recurring entries are templates only. | 10
Accounting | Budgets | Budgets | BudgetWorkspace | 90% | Prototype-complete | Approval lifecycle is local; no server planning engine. | 6
Accounting | Period Lock | Period Lock | PeriodClosing | 88% | Prototype-complete | Roles are simulated, never authenticated. | 5
Inventory | Items | Items | Items | 90% | Prototype-complete | No multi-location stock or alternative valuation methods. | 4
Inventory | Inventory Adjustments | Inventory Adjustments | InventoryAdjustments | 88% | Prototype-complete | Approval step is local only. | 1
Sales | Customers | Customers | Customers | 93% | Prototype-complete | Credit limit is recorded but not enforced at posting. | 3
Sales | Sales Orders | Sales Orders | SalesOrders | 90% | Prototype-complete | No delivery or fulfilment tracking. | 4
Sales | Invoices | Invoices | InvoiceWorkspace | 92% | Prototype-complete | No e-invoice/IRN and no payment gateway. | 5
Sales | Credit Notes | Credit Notes | CreditNotes | 88% | Prototype-complete | Refund marking is manual. | 2
Sales | Receipts | Payments Received | Receipts | 88% | Prototype-complete | No bank feed; advance liability is local. | 4
Purchases | Vendors | Vendors | Vendors | 88% | Prototype-complete | No vendor portal or statement email. | 2
Purchases | Purchase Orders | Purchase Orders | Purchases | 82% | Usable, gaps | Register header not migrated; no vendor email step. | 2
Purchases | Purchase Bills | Purchase Bills | Purchases | 82% | Usable, gaps | Register header not migrated; three-way match is partial. | 2
Purchases | Goods Receipts | Goods Receipts | GoodsReceipts | 78% | Usable, gaps | Register header not migrated; no inspection stage. | 2
Purchases | Debit Notes | Debit Notes | DebitNotes | 86% | Prototype-complete | Register header not migrated; no TDS adjustment line. | 2
Purchases | Vendor Payments | Payments Made | VendorPayments | 80% | Usable, gaps | Read-only by design; register header not migrated. | 2
Banking | Bank Accounts | Bank Accounts | Banking | 78% | Usable, gaps | No live bank feed (CSV import only). | 3
Banking | Bank Transactions | Bank Transactions | Banking | 75% | Usable, gaps | Categorisation rules are local only. | 3
Banking | Bank Reconciliation | Bank Reconciliation | BankReconciliation | 78% | Usable, gaps | Matching is suggestion-based; nothing auto-completes. | 3
Banking | Banking Settings | Banking Settings | Banking | 78% | Usable, gaps | Configuration is local only. | 3
Expenses | Expense Claims | Expense Claims | OperationalModules | 70% | Usable, gaps | No approval chain or reimbursement payout; thin tests. | 2
Expenses | Expense Categories | Expense Categories | OperationalModules | 68% | Partial | No per-category budget linkage; shared ops shell. | 2
Assets | Asset Register | Asset Register | OperationalModules | 68% | Partial | No disposal flow or revaluation. | 2
Assets | Depreciation | Depreciation | OperationalModules | 65% | Partial | One method per class; no bulk schedule run. | 2
Assets | Asset Transactions | Asset Transactions | OperationalModules | 62% | Partial | Read-only lifecycle view. | 2
Tax | GST | GST Reports | OperationalModules | 60% | Partial | Read-only monitor; no GSTR-1/3B file generation. | 2
Tax | TDS | TDS Reports | OperationalModules | 60% | Partial | Read-only monitor; no challan or return generation. | 2
Reports | Transaction Register | Transaction Register | TransactionRegister | 78% | Usable, gaps | No drill-through to every source type. | 1
Reports | Balance Sheet | Balance Sheet | BalanceSheet | 82% | Usable, gaps | Totals mix posted journals with demo seeds. | 1
Reports | Profit & Loss | Financial Reports | OperationalModules | 68% | Partial | Shares the reports index; no comparative periods. | 1
Reports | Cash Flow Statement | Financial Reports | OperationalModules | 68% | Partial | Same page as Profit & Loss; indirect method only. | 1
Reports | Trial Balance | Trial Balance | InvoiceWorkspace | 70% | Usable, gaps | No grouping or level control. | 1
Reports | General Ledger | General Ledger | GeneralLedgerPro | 86% | Prototype-complete | No file export. | 1
Reports | Account Ledger | General Ledger | GeneralLedgerPro | 86% | Prototype-complete | Same page as General Ledger. | 1
Reports | Day Book | Day Book | DayBook | 80% | Usable, gaps | Read-only, no export. | 1
Reports | Purchase Reports | Purchase Reports | PurchaseReports | 66% | Partial | Thin scope; register header not migrated. | 1
Reports | Audit Log | Audit Log | AuditLog | 70% | Usable, gaps | Read-only list; no module filters. | 1
Settings | Settings Center | Settings Center | SettingsWorkspace | 72% | Usable, gaps | 18 sections, local storage only. | 2
Settings | Company | Company | OrgList / CompanySetup | 70% | Usable, gaps | No delete or merge of organisations. | 1
Settings | Branch | Branches | OrgList | 70% | Usable, gaps | Same shell as Company. | 1
Help | Help Center | Help Center | HelpCenter | 65% | Partial | Static guidance content. | 1

## Next actions
Remaining work, in priority order
Priority | Area | Action | Why it matters | Where
P0 | Router | Replace the catch-all placeholder screen with an explicit route map or a real not-found page. | Any new page name silently renders placeholder copy instead of failing loudly. | src/App.jsx (page dispatch)
P0 | Dead code | Delete the unreachable legacy GeneralLedger component, ledgerRows and the Panel/Donut/stats helpers. | Two General Ledger implementations confuse the next reader of the router. | src/App.jsx
P0 | Purchases | Migrate the five purchase registers onto the shared register row: Purchase Orders, Purchase Bills, Goods Receipts, Debit Notes, Vendor Payments. | They are the last registers on the old header, so the module reads as a different product. | src/Purchases.jsx, GoodsReceipts.jsx, DebitNotes.jsx, VendorPayments.jsx
P0 | Expenses, Assets, Tax | Move the eight operational pages off the opsPage/opsHead shell onto the register pattern. | Largest remaining visual inconsistency: pre-register headings, spacing and tables. | src/OperationalModules.jsx, operational-modules.css
P0 | Banking | Align the four banking pages with the same page container and register row. | Same container inconsistency as the operational pages. | src/Banking.jsx, BankReconciliation.jsx, BankingSettings.jsx
P0 | Reports | Bring Transaction Register, Trial Balance, Purchase Reports and Audit Log onto the shared container. | Report pages carry their own padding and headers. | src/TransactionRegister.jsx, PurchaseReports.jsx, AuditLog.jsx
P1 | Tests | Raise the thin suites: operational-modules-ui, settings-ui and help-center, against the depth of inventory-adjustments (432 lines). | The least tested areas are exactly where the functional gaps are. | tests/
P1 | Tax | Turn the GST and TDS monitors into filing preparation output. | Statutory filing is the purpose of the module; both pages are read-only today. | src/OperationalModules.jsx
P1 | Assets | Add disposal and revaluation flows with their postings. | Book value is left wrong once an asset is sold or revalued. | src/operations-store.js
P1 | Expenses | Add the approval chain and the reimbursement payout posting. | Claims stop at creation; nothing settles them. | src/operations-store.js
P1 | Chart of Accounts | Add .xlsx import beside the existing CSV path. | Named as a production gap in the roadmap. | src/account-master.js
P1 | Reports | Add file export where it is missing: General Ledger, Day Book and Trial Balance. | Every other register can export; these three cannot. | src/GeneralLedgerPro.jsx, DayBook.jsx
P1 | Docs | Refresh the roadmap P1 list: it still asks to build purchase bills, vendors, vendor payments and debit notes, which now exist. | A resuming assistant acts on stale guidance. | docs/KNOWN-GAPS-AND-ROADMAP.md
P2 | Production | Move persistence behind an authenticated API with immutable posted journals and server-enforced periods. | The prototype stores everything in the browser, so no control can be enforced client-side. | docs/KNOWN-GAPS-AND-ROADMAP.md
P2 | Handover | Add this completion report to the knowledge package index and manifest. | Gives the next assistant one place to see what is finished and what is left. | docs/README.md, docs/project-manifest.json